## Sheet1
Week | Goal | M | T | W | T | F | Justas | Jim | Ashhal | Patrick | Progress Log
4/2-4/6 | Planning |  |  | Ashhal out | Ashhal out | Ashhal out |  |  |  |  | Spent four days planning out how the heck we're going to turn this into a working product. 10/4 would recommend.
4/9-4/13 | Basic Functionality |  | Everyone out | Everyone out |  | Jim out | training.py | behavior.py | behavior.py | behavior.py
4/16-4/20 | Expanded Functionality | [5 empty] | training.py | virtual_market.py | behavior.py | behavior.py
4/23-4/27 | Refinement | Patrick out | Patrick out | Patrick maybe |  | Jim out | training.py | vm, behavior | vm, behavior
4/30-5/4 | Final Adjustments | Jim out |  |  |  |  | gui.py | Cleanup | Cleanup | Cleanup