## Sheet1
StockBot Log | 1/8-1/12 | 1/15-1/19 | 1/22-1/26 | 1/29-2/2 | 2/5-2/9 | 2/12-2/16 | 2/19-2/23 | 2/26-3/2 | 3/5-3/9 | 3/12-3/16 | 3/19-3/23
| Set up PyCharm, installed and tested libraries. Contacted mentor. Set up repo. | Working on creating a virtual market, an environment for our bot to tests its skills in an interactive manner in the future. Creating an LSTM network (Long Short Term Memory) to go through a string of characters and predict what the next character will be. | Debugged the network (with some success). Completed the virtual market and changed it to an object-oriented setup. Examined financial indicators. Figured out how to do exponential regression in python. | Created a test class to use the model and virtual market. Debugging the finance class and setting up as an actual class (same with virtual market). Discussed options for determining which stocks to purchase in the test class (e.g., investor strategies). researched backend of the stocks to see whther we should buy or sell. Visualization of Aroon ADX Bolinger Squeeze and accumulation distribution are available at http://stockcharts.com/h-sc/ui | Started the week with a serious discussion of the future of the project and drafted a lengthy response to Mr. Pal's feedback from the week before. Looked into libraries we could use to scrape financial data off of the Wall Street Journal. Started researching what fundamentals would help determine which stocks we should invest in. More work on fixing the neural network. Preliminary research into regressors and other algorithms we could use to determine how many stocks to buy. | Considered Mr. Pal's feedback based on our response. Divided the work to come into four pieces and began to research options to tackle each portion. Ashhal is looking into scraping data that Alpha Vantage doesn't give us from sites like the Wall Street Journal. Patrick is figuring out what of that data could be useful to us in picking stocks. Justas continues to refine the neural network. Jim is exploring how to calculate a position size (how many shares to buy) based on the network's prediction. | Ashhal decided to move on from trying to use Scrapy with the school computers and switched to using a laptop. Patrick continued to explore fundamental indicators to pick stocks. Justas started to examine alternative structures for the neural network given the thus far high inaccuracy of the LSTM. Jim started writing up algorithms in virtual market to buy and sell specific amounts of stocks based on the network's prediction. The group also discussed how to use more data than just price movement in the neural network. No word from Pal this week, but we gave him a heads up about what we're doing. | Ashhal spent an ungodly amount of time trying to set up the laptop he got last week. Patrick worked on converting his notes on fundamental indicators to a table that shows what readings for each indicator suggest that a company is worth investing in (e.g., does a high or low P/E ratio mean we should buy?). Justas began to explore reinforcement learning (e.g., policy-based model) in place of the LSTM and got csv files for extra economic data. Jim worked on coding the deliverable by setting up a loop that will go through 2017 and trade MSFT stock using the methods we've written so far. | With Scrapy now installed (HALLELUJAH!), Ashhal began learning how to use the library and did some preliminary testing. Justas explored intraday trading and developed an automated means of collecting intraday data for nearly 300 frequently-traded companies from Alpha Vantage. Patrick continued his analysis of fundamental indicators. Jim started to work on integrating deliverable.py with the model. There were a lot of errors all around (especially with Alpha Vantage), so much of the time this week was spent on debugging. | Now that he has learned how to use Scrapy, Ashhal tested retrieving financial data from the Wall Street Journal. Patrick wrote a company class to store information about each company's fundamentals and a compare class to consider these company objects in relation to each other. Justas wrote up a plan for our next deliverable and explored options for moving ahead with a UI. Jim rewrote the finance class so that it can retrieve info about any indicator at any specific date or time for easier use in the data_loader class Justas wrote. | Ashhal was successful in getting financials from WSJ this week, a big step forward into narrowing down company lists. Patrick continued to work on company and compare, considering merging them to improve the structure of his code. Justas investigated how to use Dash to create visualizations of what our model is doing in preparation for our next deliverable. Jim added methods to finance that can calculate indicators using just the price data AV provides so that we don't lose the data Justas has already compiled in the past couple of weeks.